## Read Me
P6 PRO ACADEMY — SAMPLE PROJECT WORKBOOK
Adding Cost with User-Defined Fields · Baselining · Reading the Progress Line in Primavera P6
Running example: “Riverside Single-Storey Rear Extension” — 10 activities · 33-day critical path
What this workbook is for
A ready-to-use sample project for your YouTube tutorial. Build it once in P6, then use it to demonstrate (1) loading cost with User-Defined Fields, (2) baselining, and (3) reading the Progress Line. All durations, logic and costs are provided so you (or a student) can reproduce the exact result on screen.
How the tabs are organised
1. Activity List | The 10 activities, durations, logic links and the 3 cost UDFs (Material / Labour / Non-Labour). Type these into P6.
2. CPM Schedule Check | Live forward/backward pass (ES, EF, LS, LF, Total & Free Float) using the True Troop UK convention. Your answer key — confirms the 33-day critical path.
3. Cost Summary | Cost split by category with a chart. Use it to sense-check the UDF totals P6 rolls up to WBS / project level.
4. Part A – Variance | PART A of the exercise: the 2 changes (1 duration, 1 logic), the rescheduled finish dates and the expected variance — what slipped and what came forward.
5. Part B – Progress Line | PART B of the exercise: the status update (data date + % complete) that makes the Progress Line bend, and how to read it.
6. P6 Step-by-Step | The full click-path in P6, start to finish — project setup, activities, UDFs, baseline, the 2 changes, statusing and displaying the Progress Line.
Important notes before you film
• | All costs and dates are ILLUSTRATIVE sample data for teaching — they are not a real estimate.
• | Cost loaded via UDFs is NOT time-phased: it will not appear in the resource/cost usage profile or drive earned value. Use it for quick, high-level cost tagging only. Tab 6 explains the alternatives (Resources and Expenses).
• | P6 sign convention (important on camera): date Variance = Baseline − Current. So an activity finishing LATER than baseline shows a NEGATIVE variance (behind); EARLIER shows POSITIVE (ahead). Confirm the sign on one known activity before you record.
• | Progress Line: bends to the LEFT of the data date = BEHIND schedule; to the RIGHT = AHEAD. It only bends once you record progress and move the data date (see Part B).
Prepared by DR FRANCIS OSADARE · THE TRUE TROOP CONSULTING LTD · home.thetruetroop.com

## 1. Activity List
1. ACTIVITY LIST — Riverside Rear Extension (10 activities)
Type these into P6 exactly as shown. Costs are illustrative inputs you enter manually into the 3 UDF columns.
Activity ID | Activity Name | Orig. Dur (d) | Predecessor (Link) | Rel. Type | Material Cost | Labour Cost | Non-Labour Cost | Total Cost (£)
A1000 | Mobilisation & Site Setup | 2 | — | Start | 500 | 800 | 1200 | 2500
A1010 | Excavate Foundations | 3 | A1000 | FS | 200 | 1500 | 2400 | 4100
A1020 | Pour Foundations & Cure | 4 | A1010 | FS | 3500 | 1800 | 600 | 5900
A1030 | Blockwork Walls | 6 | A1020 | FS | 6000 | 4200 | 400 | 10600
A1040 | Roof Structure & Covering | 5 | A1030 | FS | 5500 | 3500 | 800 | 9800
A1050 | Windows & External Doors | 2 | A1040 | FS | 4000 | 1000 | 0 | 5000
A1060 | First Fix M&E | 3 | A1040 | FS | 1800 | 2100 | 0 | 3900
A1070 | Plastering | 4 | A1050, A1060 | FS | 1200 | 2800 | 300 | 4300
A1080 | Second Fix M&E & Fit-out | 4 | A1070 | FS | 2500 | 2800 | 0 | 5300
A1090 | Snagging & Handover | 2 | A1080 | FS | 150 | 900 | 0 | 1050
PROJECT TOTAL |  |  |  |  | 25350 | 21400 | 5700 | 52450
Legend: | Gold-tinted cells = values you type in manually (the 3 cost UDFs). FS = Finish-to-Start. A1050 (Windows) carries 1 day of float; all others are critical.

## 2. CPM Schedule Check
2. CPM SCHEDULE CHECK — Answer Key (True Troop UK convention)
Convention: EF = ES + Dur · Successor ES = predecessor EF + lag · LS = LF − Dur · Total Float = LS − ES · Free Float = successor ES − EF. Day 0 = project start.
Activity ID | Activity Name | Dur | Predecessors | ES | EF | LS | LF | Total Float | Free Float | Critical?
A1000 | Mobilisation & Site Setup | 2 | — | 0 | 2 | 2 | 0 | 0 | 0 | CRITICAL
A1010 | Excavate Foundations | 3 | A1000 | 2 | 5 | 5 | 2 | 0 | 0 | CRITICAL
A1020 | Pour Foundations & Cure | 4 | A1010 | 5 | 9 | 9 | 5 | 0 | 0 | CRITICAL
A1030 | Blockwork Walls | 6 | A1020 | 9 | 15 | 15 | 9 | 0 | 0 | CRITICAL
A1040 | Roof Structure & Covering | 5 | A1030 | 15 | 20 | 20 | 15 | 0 | 0 | CRITICAL
A1050 | Windows & External Doors | 2 | A1040 | 20 | 22 | 23 | 21 | 1 | 1 | float
A1060 | First Fix M&E | 3 | A1040 | 20 | 23 | 23 | 20 | 0 | 0 | CRITICAL
A1070 | Plastering | 4 | A1050, A1060 | 23 | 27 | 27 | 23 | 0 | 0 | CRITICAL
A1080 | Second Fix M&E & Fit-out | 4 | A1070 | 27 | 31 | 31 | 27 | 0 | 0 | CRITICAL
A1090 | Snagging & Handover | 2 | A1080 | 31 | 33 | 33 | 31 | 0 | 0 | CRITICAL
Schedule summary
Project duration: |  | 33 | working days
Critical path: |  | A1000 → A1010 → A1020 → A1030 → A1040 → A1060 → A1070 → A1080 → A1090 (A1050 has 1 day of float)

## 3. Cost Summary
3. COST SUMMARY — by category
Pulled live from the Activity List. In P6 these are the WBS/project roll-ups of your 3 cost UDFs.
Cost Category | Amount (£) | % of Total
Material | 25350 | 48.33%
Labour | 21400 | 40.8%
Non-Labour | 5700 | 10.87%
TOTAL | 52450 | 100%

## 4. Part A - Variance
4. PART A — BASELINE & VARIANCE (the 2 changes)
The two changes to make AFTER baselining
Change 1 — DURATION | A1030 Blockwork Walls: extend duration 6d → 9d (e.g. weather + extra coursing). A1030 is critical, so everything downstream is pushed out.
Change 2 — LOGIC | A1050 Windows & External Doors: re-link its predecessor from A1040 (Roof) to A1030 (Blockwork) — frames go into the openings earlier. Windows now comes forward and gains float.
Expected result after rescheduling (F9)
Activity ID | Activity Name | Baseline Finish (d) | Revised Finish (d) | Variance (d) | What you'll see
A1000 | Mobilisation & Site Setup | 2 | 2 | 0
A1010 | Excavate Foundations | 5 | 5 | 0
A1020 | Pour Foundations & Cure | 9 | 9 | 0
A1030 | Blockwork Walls | 15 | 18 | -3 | Late − the changed activity
A1040 | Roof Structure & Covering | 20 | 23 | -3 | Late (pushed by A1030)
A1050 | Windows & External Doors | 22 | 20 | 2 | AHEAD — came forward 2d
A1060 | First Fix M&E | 23 | 26 | -3 | Late (critical chain)
A1070 | Plastering | 27 | 30 | -3 | Late (critical chain)
A1080 | Second Fix M&E & Fit-out | 31 | 34 | -3 | Late (critical chain)
A1090 | Snagging & Handover | 33 | 36 | -3 | PROJECT 3 DAYS LATE
P6 sign convention: Variance = Baseline Finish − Current Finish. A NEGATIVE value = finishing LATER than baseline (behind, red). A POSITIVE value = finishing EARLIER (ahead, green). Add columns ‘BL Project Finish’ and ‘Variance – BL Project Finish Date’ in P6 to see this.
Revised forward-pass helper (Change 1 + Change 2 applied)
ID | Dur(rev) | ES | EF
A1000 | 2 | 0 | 2
A1010 | 3 | 2 | 5
A1020 | 4 | 5 | 9
A1030 | 9 | 9 | 18
A1040 | 5 | 18 | 23
A1050 | 2 | 18 | 20
A1060 | 3 | 23 | 26
A1070 | 4 | 26 | 30
A1080 | 4 | 30 | 34
A1090 | 2 | 34 | 36

## 5. Part B - Progress Line
5. PART B — THE PROGRESS LINE (status update)
Reset to the baseline schedule, then apply this status. The data date moves to Day 21 and you record % complete. Now the Progress Line bends — left of the data date = behind, right = ahead.
Status to record (Data Date = end of Day 21)
Activity ID | Activity Name | Baseline (d) | Status | Actual % Complete | Planned % @ DD | Ahead/Behind | Progress Line
A1000 | Mobilisation & Site Setup | 2 | Complete | 100% | 100% | — | On the line
A1010 | Excavate Foundations | 3 | Complete | 100% | 100% | — | On the line
A1020 | Pour Foundations & Cure | 4 | Complete | 100% | 100% | — | On the line
A1030 | Blockwork Walls | 6 | Complete | 100% | 100% | — | On the line
A1040 | Roof Structure & Covering | 5 | Complete | 100% | 100% | — | On the line
A1050 | Windows & External Doors | 2 | In progress | 90% | 50% | AHEAD | Bends RIGHT →
A1060 | First Fix M&E | 3 | In progress | 10% | 33% | BEHIND | ← Bends LEFT
A1070 | Plastering | 4 | Not started | 0% | 0% | — | —
A1080 | Second Fix M&E & Fit-out | 4 | Not started | 0% | 0% | — | —
A1090 | Snagging & Handover | 2 | Not started | 0% | 0% | — | —
How to read it on screen
• | Windows (A1050) is 90% done but only ~50% was planned by the data date → the line juts to the RIGHT (ahead).
• | First Fix (A1060) is only 10% done vs ~33% planned → the line juts to the LEFT (behind). And because A1060 is on the critical path, rescheduling now pushes the finish out — the visual (Progress Line) and the numbers (Variance) agree.
• | Completed activities sit fully progressed; not-started activities sit on the line. The zig-zag between A1050 and A1060 is your teaching moment.
• | Display options: base the line on % Complete (most intuitive) or Remaining Duration. Show the baseline bars underneath so the audience can see plan vs actual at a glance.

## 6. P6 Step-by-Step
6. P6 STEP-BY-STEP — from empty project to Progress Line
Menu wording varies slightly by P6 version — paths below are for P6 Professional.
A. Create the project & activities
1 | EPS → right-click → Add Project. Set a Planned Start (e.g. Mon 01 Sep 2025) and the default calendar (Standard 5-day week).
2 | Open the Activities window. Add the 10 activities from Tab 1 with their IDs, names and Original Durations.
3 | Set each activity’s relationships (the Predecessor / Relationships tab). All links are Finish-to-Start; A1070 has two predecessors (A1050 and A1060).
4 | Press F9 → Schedule. Confirm total duration = 33 days and the critical path matches Tab 2.
B. Load cost using 3 User-Defined Fields
1 | Enterprise → User Defined Fields. Set Subject Area = Activities.
2 | Add three fields, Data Type = Cost: ‘Material Cost’, ‘Labour Cost’, ‘Non-Labour Cost’.
3 | Back in the Activities window, right-click the column header → Columns. Add the three UDF columns (and an optional UDF ‘Total’ if you create one).
4 | Type the costs from Tab 1 into each activity. Group by WBS to watch P6 roll the UDF cost up to summary level.
5 | TEACHING POINT — other ways to add cost: (1) RESOURCES: build Labour / Non-Labour / Material resources in the Resource dictionary, assign units & price/unit → time-phased cost, resource histograms, levelling and earned value. (2) EXPENSES: the activity Expenses tab for lump-sum items (permits, plant hire, materials) with cost accounts and accrual type. UDFs are quickest but are NOT time-phased and do not drive EVM.
C. Baseline the programme
1 | Project → Maintain Baselines → Add → ‘Save a copy of the current project as a new baseline’. Name it e.g. ‘B0 – Original Plan’.
2 | Project → Assign Baselines. Set the Project Baseline (and your Primary user baseline) to ‘B0 – Original Plan’.
3 | Show the baseline bars: View → Bars → tick the Project Baseline bar so plan vs current is visible.
D. PART A — make the 2 changes & read variance
1 | Change 1 (DURATION): set A1030 Blockwork Walls Original Duration 6 → 9.
2 | Change 2 (LOGIC): open A1050 Windows, change its predecessor from A1040 (FS) to A1030 (FS).
3 | Press F9 → Schedule.
4 | Add columns: ‘BL Project Finish’ and ‘Variance – BL Project Finish Date’ (and the Start equivalents).
5 | Read the result (Tab 4): the critical chain shows a negative variance (3 days late); Windows shows a positive variance (2 days ahead). Negative = behind, positive = ahead.
E. PART B — status the job & show the Progress Line
1 | First, remove the Part A changes (or re-open your saved baseline copy) so you start from the 33-day plan.
2 | Set the Data Date to end of Day 21: Project → (Schedule / F9 dialog) set Current Data Date, or drag the data date line.
3 | Status the activities from Tab 5: mark A1000–A1040 Complete; set A1050 = 90% and A1060 = 10%; leave A1070–A1090 not started. Use Physical % Complete (Activity Details → Status).
4 | Press F9 → Schedule with the new data date.
5 | Display the Progress Line: in the Gantt, toggle the Progress Line (View → Gantt Chart Options → Progress Line tab, or the Progress Line toolbar button). Choose to base it on % Complete.
6 | Read it (Tab 5): the line juts RIGHT at Windows (ahead) and LEFT at First Fix (behind). Pair it with the baseline bars so the audience sees plan vs actual together.
Prepared by DR FRANCIS OSADARE · THE TRUE TROOP CONSULTING LTD · home.thetruetroop.com